PRODUCT REQUIREMENTS DOCUMENT

AI Course Assistant

Chatbot Agent

A RAG-powered AI agent that answers student questions from course content — like a personal tutor inside every course

Version 1.0  |  March 2026  |  Solo Project

Developer: 1 Person  |  2-3 Hours/Day  |  6 Weeks  |  Cost: Rs. 0

Table Of Contents

| 1. | Project Overview | 2 |
| --- | --- | --- |
| 2. | Problem Statement | 3 |
| 3. | Objectives & Success Criteria | 3 |
| 4. | Features & Scope | 4 |
| 5. | Tech Stack | 5 |
| 6. | System Architecture | 5 |
| 7. | End-to-End Task Plan | 6 |
| 8. | Non-Functional Requirements | 13 |
| 9. | Risks & Mitigations | 13 |
| 10. | MVP Scope | 14 |
| 11. | Future Enhancements | 14 |
| 12. | Conclusion | 15 |

# 1. Project Overview

Product Name: AI Course Assistant Chatbot Agent

Product Type: Solo AI/ML project — RAG-based intelligent chatbot for a learning platform

Developer: 1 person  |  Timeline: 6 weeks  |  Hours: 2-3 hours/day  |  Cost: Rs. 0

This is a smart AI chatbot that lives inside each course page on a learning platform. When a student is studying Full Stack, AI/ML, Web Dev, or any other course — they can type any question and the agent answers instantly using only that course's content. It works like a personal tutor available 24/7.

## The One Line Summary

Student types a question → Agent reads the course material → Agent answers in simple language No Googling. No waiting for a teacher. Instant answer from the course itself.

## Who Uses It

| User | How They Use It |
| --- | --- |
| Student | Asks questions about course topics while studying. Gets instant simple explanations. |
| Friend's Client (Platform Owner) | Adds the chatbot to every course page. Students stay on platform instead of leaving to Google. |
| You (Developer) | Builds, deploys, and maintains the chatbot. Adds new courses by uploading content files. |

# 2. Problem Statement

Students learning online often get stuck on concepts. When they do not understand something they have 3 bad options:

- Leave the platform and search Google — they may not come back

- Post in a forum and wait hours for a reply — learning is interrupted

- Give up and skip the concept — they miss important knowledge

The platform owner loses students because there is no instant help available. A teacher cannot be available 24/7 to answer every student's doubt.

The solution is an AI agent that reads the course content and answers student questions instantly — in simple language — without the student ever leaving the course page.

# 3. Objectives & Success Criteria

## Objectives

- Build an AI agent that answers student questions using only the course content — no made-up answers.

- Make it work for multiple courses — Full Stack, AI/ML, Web Dev — switching automatically based on which course the student is on.

- Answer in simple, easy language that a beginner can understand.

- Remember the conversation so students can ask follow-up questions naturally.

- Deploy it as a chat widget inside the friend's website — real students can use it.

## Success Criteria

The project is successful if:

- Student asks a course-related question and gets a correct, simple answer within 5 seconds.

- Agent only uses course content — never answers from outside the course material.

- Agent works for at least 3 different courses without code changes.

- Student can ask follow-up questions and agent remembers the previous conversation.

- Chat widget is visible and usable on the friend's website by real students.

- Full demo works end to end: student types question — agent reads course — student gets answer.

# 4. Features & Scope

## In-Scope Features

| Feature | Description |
| --- | --- |
| Course-aware Q&A | Agent knows which course the student is on and only answers from that course's content. |
| Simple explanations | Answers in easy beginner-friendly language. No unnecessary jargon. |
| Follow-up memory | Agent remembers the last 5-10 messages so students can ask follow-up questions. |
| Multi-course support | Works for Full Stack, AI/ML, Web Dev — just upload content file per course. |
| Out-of-scope handling | If question is outside course content, agent politely says so instead of making up an answer. |
| Chat widget UI | Floating chat box embedded inside each course page on the website. |
| Source display | Agent shows which part of the course content it used to answer — builds trust. |

## Out-of-Scope

- Voice input or voice output — text only.

- Student progress tracking or personalised learning paths.

- Grading or assignment evaluation.

- Video content understanding — text/PDF course content only.

- Multi-language support — English only in this version.

# 5. Tech Stack

All free. All beginner-friendly. All well-documented.

| Layer | Technology | Why This |
| --- | --- | --- |
| LLM (AI brain) | Groq API — Llama 3 (free) | Free, very fast, smart enough for course Q&A |
| RAG Framework | LangChain | Connects LLM with course content easily |
| Vector Database | ChromaDB (local, free) | Stores course content as searchable embeddings |
| Embeddings | HuggingFace sentence-transformers (free) | Converts text to vectors for search |
| Backend API | FastAPI (Python) | You already know this — handles all chat requests |
| Frontend | React chat widget | Simple chat box embedded in course page |
| Course Content | PDF or TXT files | One file per course — easy to add new courses |
| Environment | Python virtual env + .env file | Keeps API keys safe |

# 6. System Architecture

## How It Works — Simple View

SETUP (done once per course — you do this): Course PDF/TXT file → Split into small chunks → Convert to embeddings → Save in ChromaDB RUNTIME (every time a student asks a question): Student types question → FastAPI receives it → LangChain converts question to embedding → ChromaDB finds 3-5 most relevant course chunks → Groq LLM reads question + relevant chunks → LLM generates simple answer → FastAPI sends answer back to React chat widget → Student sees the answer in under 5 seconds

## Folder Structure

course-chatbot/ ├── backend/ │ ├── main.py ← FastAPI app (chat endpoint) │ ├── rag.py ← LangChain RAG pipeline │ ├── ingest.py ← Loads course content into ChromaDB │ ├── courses/ ← Course content files (.pdf or .txt) │ │ ├── aiml.pdf │ │ ├── fullstack.pdf │ │ └── webdev.pdf │ └── chroma_db/ ← ChromaDB stores embeddings here ├── frontend/ │ └── ChatWidget.jsx ← React chat component ├── .env ← API keys (never commit this) └── requirements.txt ← All Python dependencies

# 7. End-to-End Task Plan

This is your complete step-by-step guide from Day 1 to final demo. Every task has a clear title, part label, subtasks, and time estimate. Follow this in order and you will always know exactly what to do next.

HOW TO READ THIS PLAN: Part label shows you which area the task belongs to — Backend, ML/AI, Frontend, or DevOps Time is how long each task takes at 2-3 hours/day pace Each subtask is one clear action — complete it before moving to the next At the end of every task you have something working — never stuck with nothing to show

## WEEK 1 — Setup & First Working Chat

Goal: By end of Week 1 you can type a question in Python and get an AI answer back.

Task 1 Project Setup & Environment Part: DevOps / Setup ¦ Time: Day 1 ¦ 2-3 hours

### What you are doing

Setting up your project folder, Python environment, and installing all libraries. This is the foundation everything else builds on.

### Subtasks — do in this order

- Create a folder called course-chatbot on your Desktop

- Open terminal in that folder and create a virtual environment:  python -m venv venv

- Activate it:  venv\Scripts\activate  (Windows)

- Create requirements.txt file with these libraries:  fastapi, uvicorn, langchain, langchain-groq, langchain-community, chromadb, sentence-transformers, pypdf, python-dotenv

- Install all:  pip install -r requirements.txt

- Create a .env file and add:  GROQ_API_KEY=your_key_here

- Get free Groq API key from console.groq.com — takes 2 minutes

- Create the folder structure shown in Section 6

### How you know this task is done

You can run  python  in terminal and  import langchain  without any error.

Task 2 First Groq LLM Call Part: ML / AI ¦ Time: Day 2 ¦ 2-3 hours

### What you are doing

Make your first call to the Groq LLM API and get a response back. This proves your API key works and you understand how to talk to the AI.

### Subtasks — do in this order

- Create a file called test_groq.py in your backend folder

- Import LangChain Groq:  from langchain_groq import ChatGroq

- Create the LLM object:  llm = ChatGroq(model='llama3-8b-8192', groq_api_key=your_key)

- Send a test message:  response = llm.invoke('What is machine learning?')

- Print the response and verify you get a real answer back

- Try 3-4 different questions to get comfortable

### How you know this task is done

You type a question in Python code and Groq sends back a real answer within 2-3 seconds.

Task 3 Load Course Content into ChromaDB Part: ML / AI ¦ Time: Day 3-4 ¦ 4-5 hours

### What you are doing

This is the most important ML task. You take a course PDF or text file, split it into small chunks, convert each chunk into a vector embedding, and save everything in ChromaDB. This is the RAG setup step.

### Subtasks — do in this order

- Add a sample course content file — create aiml.txt in backend/courses/ with 20-30 lines about AI/ML basics (you can write this yourself or copy from any textbook)

- Create ingest.py file in backend/

- Load the file using LangChain TextLoader:  loader = TextLoader('courses/aiml.txt')

- Split into chunks:  splitter = RecursiveCharacterTextSplitter(chunk_size=500, chunk_overlap=50)

- Create embeddings model:  embeddings = HuggingFaceEmbeddings(model_name='all-MiniLM-L6-v2')

- Save to ChromaDB:  vectordb = Chroma.from_documents(chunks, embeddings, persist_directory='chroma_db')

- Run the script and verify chroma_db folder is created with data inside

- Test retrieval — search for a question and print the top 3 matching chunks

### How you know this task is done

You search for 'what is neural network' and ChromaDB returns the 2-3 most relevant paragraphs from your course file.

Task 4 Build the RAG Pipeline Part: ML / AI ¦ Time: Day 5-6 ¦ 4-6 hours

### What you are doing

Connect ChromaDB + Groq LLM together using LangChain. This is the full AI brain of the chatbot — question goes in, course-aware answer comes out.

### Subtasks — do in this order

- Create rag.py file in backend/

- Load ChromaDB:  vectordb = Chroma(persist_directory='chroma_db', embedding_function=embeddings)

- Create retriever:  retriever = vectordb.as_retriever(search_kwargs={'k': 3})

- Create RAG chain using LangChain RetrievalQA:  chain = RetrievalQA.from_chain_type(llm=llm, retriever=retriever)

- Test it: chain.invoke('Explain what supervised learning is')

- Verify the answer uses content from your course file — not made-up content

- Add a system prompt that says: answer in simple language, only use course content, if not in course say so

- Test 5 questions — 3 inside the course content, 2 outside — verify agent handles both correctly

### How you know this task is done

Ask a question that is in your course file — agent answers using that content. Ask something not in the file — agent says it is outside the course content.

## WEEK 2 — FastAPI Backend

Goal: By end of Week 2 you have a working API endpoint that any frontend can call to get answers.

Task 5 Build FastAPI Chat Endpoint Part: Backend / FastAPI ¦ Time: Day 8-9 ¦ 4-5 hours

### What you are doing

Wrap your RAG pipeline inside a FastAPI endpoint. This turns your Python script into a real API that a React frontend can call.

### Subtasks — do in this order

- Create main.py in backend/

- Import FastAPI and your rag.py:  from fastapi import FastAPI  |  from rag import get_answer

- Create Pydantic request model:  class ChatRequest(BaseModel): question: str, course_id: str

- Create Pydantic response model:  class ChatResponse(BaseModel): answer: str, sources: list

- Build POST endpoint:  @app.post('/chat')  def chat(request: ChatRequest)

- Inside the endpoint: call get_answer(request.question, request.course_id) and return the result

- Add CORS middleware so React can call this API from a different port

- Run the server:  uvicorn main:app --reload

- Test using FastAPI docs at http://localhost:8000/docs — send a test question

### How you know this task is done

You open http://localhost:8000/docs, send a POST request with a question, and get a JSON response with the answer.

Task 6 Add Conversation Memory Part: Backend / ML / AI ¦ Time: Day 10-11 ¦ 4-5 hours

### What you are doing

Add memory to the chatbot so it remembers the last few messages. Without this, every question is treated as a brand new conversation — student cannot ask follow-up questions.

### Subtasks — do in this order

- Update ChatRequest model to include:  session_id: str, chat_history: list

- Use LangChain ConversationBufferWindowMemory with k=5 (remember last 5 messages)

- Store session memories in a Python dictionary keyed by session_id

- Update the RAG chain to use ConversationalRetrievalChain instead of RetrievalQA

- Pass chat_history to the chain on every request

- Test follow-up questions: first ask 'what is overfitting', then ask 'give me an example of that' — verify agent understands 'that' refers to overfitting

### How you know this task is done

You ask 'what is gradient descent' then ask 'why is it important' and the agent correctly answers about gradient descent without you repeating the topic.

Task 7 Add Multi-Course Support Part: Backend / ML / AI ¦ Time: Day 12-13 ¦ 4-5 hours

### What you are doing

Make the agent work for multiple courses. Each course has its own ChromaDB collection so answers come only from the right course.

### Subtasks — do in this order

- Create content files for 3 courses: aiml.txt, fullstack.txt, webdev.txt — each with 20-30 lines of course content

- Update ingest.py to loop through all files and create a separate ChromaDB collection per course

- Name collections by course_id:  chroma_db/aiml,  chroma_db/fullstack,  chroma_db/webdev

- Update rag.py to load the correct collection based on course_id in the request

- Test: ask an AI/ML question with course_id=aiml — verify it answers from AI/ML content

- Test: ask the same question with course_id=fullstack — verify it says it is not in that course

### How you know this task is done

The same question gives different answers depending on which course_id you send. Each course only answers from its own content.

## WEEK 3 — React Chat Widget

Goal: By end of Week 3 you have a working chat UI that calls your FastAPI backend.

Task 8 Build Basic React Chat Component Part: Frontend / React ¦ Time: Day 15-16 ¦ 4-5 hours

### What you are doing

Build the chat UI — the box students type into and see answers. Keep it simple first — just make it work.

### Subtasks — do in this order

- Create React app in frontend/:  npx create-react-app chatbot  or use Vite

- Create ChatWidget.jsx component

- Add state for: messages (array), inputText (string), isLoading (boolean)

- Build the UI: scrollable message list + text input at bottom + Send button

- Style messages: user messages on right (blue), agent messages on left (gray)

- Add a loading indicator that shows while waiting for API response

- Test the UI alone first with dummy hardcoded messages before connecting to API

### How you know this task is done

You see a chat box in the browser. You can type a message and it appears in the message list with correct styling.

Task 9 Connect React to FastAPI Part: Frontend / Backend ¦ Time: Day 17-18 ¦ 4-5 hours

### What you are doing

Connect the chat UI to your FastAPI backend. When student sends a message, it goes to your API and the answer comes back and shows in the chat.

### Subtasks — do in this order

- Install axios in frontend:  npm install axios

- Create api.js file:  const API_URL = 'http://localhost:8000'

- Write sendMessage function:  axios.post('/chat', {question, course_id, session_id, chat_history})

- In ChatWidget.jsx — on Send button click: call sendMessage, show loading, display response

- Generate a random session_id when the component first loads (use Math.random())

- Pass current chat_history with every request

- Handle errors — if API fails, show a friendly error message in the chat

- Test full flow: type a question, see loading spinner, see answer appear

### How you know this task is done

You type a real question in the browser, it calls your FastAPI, and the AI answer appears in the chat within 5 seconds.

Task 10 Polish Chat UI Part: Frontend / React ¦ Time: Day 19-20 ¦ 3-4 hours

### What you are doing

Make the chat widget look professional and feel smooth to use.

### Subtasks — do in this order

- Add timestamps to each message

- Add course name display at the top of the chat (e.g. 'AI/ML Course Assistant')

- Make Enter key send the message (not just the button)

- Auto-scroll to latest message after each response

- Add a welcome message when chat first opens: 'Hi! I am your AI/ML course assistant. Ask me anything about this course.'

- Add a character that shows agent is typing (three dots animation) while waiting

- Make the widget responsive — works on mobile screen too

### How you know this task is done

The chat feels smooth and professional. Someone else can use it without any explanation needed.

## WEEK 4 — Real Course Content & Integration

Goal: By end of Week 4 the chatbot works with real course content from your friend's platform.

Task 11 Add Real Course Content Part: ML / AI ¦ Time: Day 22-23 ¦ 4-5 hours

### What you are doing

Replace your test content files with real course content from your friend's platform. This makes the chatbot actually useful for real students.

### Subtasks — do in this order

- Get course content from your friend — PDFs, slides, or text documents for each course

- If content is in PDF: update ingest.py to use PyPDFLoader instead of TextLoader

- If content is in slides: export as PDF first, then use PyPDFLoader

- Run ingest.py for each course — verify ChromaDB is populated with real content

- Test with 10 real questions a student might ask about each course

- Identify any weak answers and improve the system prompt to handle them better

- Adjust chunk_size if needed — try 300 or 700 instead of 500 if answers are not good

### How you know this task is done

Ask 10 real student questions. At least 8 out of 10 get correct, helpful answers from the real course content.

Task 12 Integrate with Friend's Website Part: Frontend / Backend ¦ Time: Day 24-25 ¦ 4-5 hours

### What you are doing

Embed your chat widget inside your friend's existing website. The widget should appear on every course page and automatically know which course it is on.

### Subtasks — do in this order

- Share your ChatWidget.jsx with your friend or add it to his codebase directly

- Pass course_id as a prop to the widget:  <ChatWidget courseId='aiml' />

- On friend's website — add the widget to each course page with the correct course_id

- Test that AI/ML course page shows AI/ML answers, Full Stack page shows Full Stack answers

- Make widget appear as a floating button at bottom right — click to open, click to close

- Test on mobile browser — verify it works and looks good

### How you know this task is done

The chat widget is visible on your friend's website. A real student can open it and ask a course question and get a correct answer.

## WEEK 5 — Testing & Edge Cases

Goal: By end of Week 5 the chatbot handles all edge cases and is ready for real students.

Task 13 Test All Edge Cases Part: Backend / ML / AI ¦ Time: Day 29-30 ¦ 4-5 hours

### What you are doing

Systematically test every way the chatbot could fail or give a bad answer and fix each issue.

### Subtasks — do in this order

- Test out-of-scope questions: 'What laptop should I buy?' — verify agent declines politely

- Test very short questions: 'what' — verify agent asks for clarification

- Test very long questions — verify agent handles them without crashing

- Test questions in wrong course context — verify agent says content not found

- Test follow-up questions across 10 messages — verify memory works correctly

- Test what happens when Groq API is slow — verify loading state shows correctly

- Fix any issues found and retest

### How you know this task is done

All edge cases handled gracefully. No crashes. No wrong answers from outside course content.

Task 14 Improve Answer Quality Part: ML / AI ¦ Time: Day 31-32 ¦ 4-5 hours

### What you are doing

Fine-tune the system prompt and RAG settings to make answers better — simpler, more accurate, better structured.

### Subtasks — do in this order

- Collect 20 sample questions from each course

- Rate each answer: Good / Acceptable / Poor

- For Poor answers: identify if problem is retrieval (wrong chunks found) or generation (LLM gave bad answer)

- If retrieval problem: adjust chunk_size, chunk_overlap, or k (number of chunks retrieved)

- If generation problem: improve system prompt — be more specific about tone, length, format

- Add instruction to system prompt: 'Always give an example when explaining a concept'

- Retest all 20 questions and verify improvement

### How you know this task is done

At least 18 out of 20 sample questions get Good or Acceptable answers.

## WEEK 6 — Demo & Delivery

Goal: By end of Week 6 the project is fully documented, demo-ready, and delivered to your friend's client.

Task 15 Write README & Documentation Part: DevOps / Docs ¦ Time: Day 36-37 ¦ 3-4 hours

### What you are doing

Write clear documentation so anyone can set up and run your project. This is also what goes on your GitHub and resume.

### Subtasks — do in this order

- Create README.md with: project description, tech stack, setup instructions, how to add a new course

- Document all API endpoints with example requests and responses

- Write how-to-add-course guide: step by step for your friend to add new courses himself

- Add architecture diagram (simple text diagram is fine)

- Push everything to GitHub with a clean commit history

### How you know this task is done

Someone who has never seen your project can read the README and set it up in under 30 minutes.

Task 16 Prepare Demo Part: DevOps / Presentation ¦ Time: Day 38-40 ¦ 3-4 hours

### What you are doing

Prepare a live demo showing the chatbot working end to end. This is what you show to your friend's client, your college, and in job interviews.

### Subtasks — do in this order

- Prepare 5 demo questions per course that show the chatbot at its best

- Record a 2-3 minute screen recording: open website, open chatbot, ask 3-4 questions, show answers

- Prepare a 60-second verbal explanation: what the project does, how it works, what tech you used

- Test the live demo 3 times to make sure nothing crashes during presentation

- Have a backup plan — if live demo fails, show the screen recording

### How you know this task is done

You can demo the project confidently in under 3 minutes to anyone — client, professor, or interviewer.

## Full Timeline Summary

| Week | Tasks | Part | Total Time |
| --- | --- | --- | --- |
| Week 1 | Task 1: Setup, Task 2: First LLM call, Task 3: ChromaDB, Task 4: RAG pipeline | ML / AI + Setup | 10-15 hrs |
| Week 2 | Task 5: FastAPI endpoint, Task 6: Memory, Task 7: Multi-course | Backend + ML/AI | 12-15 hrs |
| Week 3 | Task 8: Chat UI, Task 9: Connect API, Task 10: Polish UI | Frontend | 11-14 hrs |
| Week 4 | Task 11: Real content, Task 12: Website integration | ML/AI + Frontend | 8-10 hrs |
| Week 5 | Task 13: Edge cases, Task 14: Answer quality | ML/AI + Testing | 8-10 hrs |
| Week 6 | Task 15: README, Task 16: Demo prep | Docs + Delivery | 6-8 hrs |
| TOTAL | 16 tasks — full working product | All parts | 55-72 hrs |

# 8. Non-Functional Requirements

| Requirement | Target |
| --- | --- |
| Response time | Answer returned within 5 seconds of student asking |
| Accuracy | At least 80% of course-related questions answered correctly |
| Out-of-scope handling | 100% of out-of-scope questions declined politely — never makes up answers |
| Memory | Remembers last 5 messages in each conversation session |
| Multi-course | Works correctly for at least 3 courses without code changes |
| Cost | Rs. 0 — all free tier services throughout the project |
| Uptime | Works reliably during demo — no crashes on normal usage |

# 9. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Groq API gives wrong answers | Improve system prompt. Add 'only use provided context' instruction. Test with 20 questions. |
| ChromaDB retrieves wrong chunks | Tune chunk_size and k. Try different embedding models. Add more content to weak areas. |
| React widget breaks on friend's website | Test early in Week 4. Use simple CSS. Avoid conflicts with existing styles. |
| Course content is in unusual format | Convert all content to PDF or TXT before ingesting. PyPDF handles most formats. |
| Memory makes context too long | Limit to last 5 messages only. Clear session after 20 exchanges. |
| Friend's website uses different tech stack | ChatWidget is a simple React component — can be converted to plain HTML/JS if needed. |

# 10. MVP Scope

## Included in MVP

- RAG pipeline that reads course content and answers questions from it only.

- FastAPI chat endpoint accepting question and course_id.

- Conversation memory for follow-up questions within same session.

- Multi-course support for at least 3 courses.

- React chat widget embedded on course pages.

- Out-of-scope question handling.

- Working demo on friend's website with real students.

## Excluded from MVP

- Voice input or output.

- Student progress tracking.

- Admin dashboard for adding courses without code.

- Analytics on most asked questions.

- Multi-language support.

# 11. Future Enhancements

| Enhancement | Description |
| --- | --- |
| Admin dashboard | Upload new course PDFs through a UI — no code needed to add courses. |
| Question analytics | Track most common questions per course — helps improve course content. |
| Confidence score | Show how confident the agent is — low confidence triggers 'ask your teacher' suggestion. |
| Voice input | Student speaks question — converted to text — agent answers. |
| Multi-language | Answer in Hindi or Gujarati for students who prefer regional language. |
| Quiz generation | Agent generates practice questions from course content to test student knowledge. |

# 12. Conclusion

This PRD describes an AI Course Assistant Chatbot that gives students instant, accurate answers from their course content — 24/7 — without leaving the course page.

The project is built solo over 6 weeks at 2-3 hours per day at zero cost. It uses LangChain, ChromaDB, Groq, FastAPI, and React — a modern, industry-standard AI stack that looks excellent on a resume.

The 16-task plan gives you a clear path from Day 1 to final demo. Every task ends with something working. You always know exactly what to do next.

At the end you will have a real product deployed on a real client's website — used by real students. That is stronger than any academic project.

Solo Project ¦ 6 Weeks ¦ Rs. 0 ¦ 16 Tasks ¦ Real Client ¦ Real Students LangChain + ChromaDB + Groq + FastAPI + React